## README
Ezurio – Requirements & Observations Tracker
Oct 19–21, 2026 onsite discovery (Gateworks SLO + Irvine). INTERNAL working file.
Tabs
1 Requirements – candidate requirements seeded from the engagement letter 'Key Areas of Focus'. Status = Hypothesis until validated onsite. Add rows as you go; keep IDs sequential.
2 Observations – raw observation log by session (what we saw/heard). Link each to a requirement ID where relevant.
3 Irvine Backlog – optimization ideas for Irvine with value/effort; cross-check against the Azure DevOps backlog to avoid duplicates.
4 GWTrack Features – feature inventory captured during the GWTrack demo (what exists, where it should live: GWTrack / NetSuite / Arena / MES).
5 Option Scoring – weighted scoring of system Options A (GWTrack), B (Manufacturing Mobile / Advanced Mfg), C (3rd-party MES / SuiteApp). Footprint options are NOT scored onsite.
6 Open Items – follow-ups, documents requested and owners.
Conventions
Priority: Must / Should / Could (MoSCoW). Fit: Native / Config / Custom / Gap / TBD.
ITAR/CUI flag: Y if the capability/data is potentially controlled – do not share the underlying detail with non-US persons until compliance confirms.
Confidentiality: no references to acquisition activity, a third site or consolidation anywhere in this file.

## 1 Requirements
Req ID | Area | Requirement (what the future system must do) | Source | Site | Session | Current state: GWTrack | Current state: Irvine (NetSuite/MM) | Priority | Fit A: GWTrack | Fit B: NetSuite MM/Adv Mfg | Fit C: 3rd-party MES/SuiteApp | ITAR/CUI flag | Owner | Status | Notes / evidence
REQ-001 | Work execution | Release work orders to the floor with routing, work instructions and revision control | EL focus: GWTrack fit | Both | 1.3 / 3.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-002 | Work execution | Operators start / pause / complete operations at the station with scan-driven transactions | EL focus: MM timekeeping | Both | 1.3 / 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-003 | Work execution | Enforce operation sequence and validations (no out-of-sequence or missing-prior-step completions) | EL focus: process control gaps | Both | 1.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-004 | Work execution | Handle partial quantities and rework loops per operation | MM process outline | Irvine | 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-005 | Material control | Prevent / warn on starting a run without sufficient committed component material | EL focus: material availability checks | Irvine | 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-006 | Material control | Support kitting / staging with one-WO-per-location control and visibility of under-picked items | Irvine WMS process | Irvine | 3.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-007 | Material control | Issue / backflush components with accurate inventory detail (bin / lot) | Irvine WMS process | Both | 1.3 / 3.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-008 | Material control | Manage substitutions / alternates and shortages with expedite visibility | Ops walk | Both | 1.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-009 | Costing | Block or flag production when an assembly has no standard cost; maintain standard cost with approvals | EL focus: standard cost enforcement | Irvine | 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-010 | Costing | Post WIP, scrap, labor and variances to NetSuite accurately and on time | Ops walk | Both | 1.4 / 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-011 | Labor / timekeeping | Capture labor by operation/job (badge-in, pause, end) including indirect, rework and multi-operator time | EL focus: timekeeping gaps | Both | 1.4 / 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-012 | Labor / timekeeping | Provide labor efficiency and cost reporting; hand-off to payroll if required | EL focus: timekeeping gaps | Both | 1.4 / 3.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-013 | Traceability | Maintain lot / serial / as-built genealogy and answer containment queries quickly | GWTrack features | Gateworks | 1.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-014 | Traceability | Retain test results and operator / equipment records per unit | GWTrack features | Gateworks | 1.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-015 | Quality | Capture defects at point of work with coded reasons and produce defect heatmaps | EL focus: quality tracking | Both | 1.4 / 3.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-016 | Quality | Manage NCR / rework / scrap disposition integrated to inventory and cost | EL focus: quality tracking | Both | 1.4 / 3.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-017 | Quality | Track customer returns (RMA) from receipt through disposition with trace to original build | EL focus: manual RMA | Both | 1.4 / 3.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-018 | Quality | Support corrective action (CAPA / 8D) and audit-ready quality records | Ops walk | Gateworks | 1.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-019 | Inventory / WMS | Post-production reconciliation of issued vs. actual components without manual template/import steps | Irvine dekit process | Irvine | 3.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-020 | Inventory / WMS | Prevent partial-pick side effects (task closes / reverse picks) or handle them gracefully | Irvine WMS process | Irvine | 3.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-021 | Engineering / PLM | Receive BOM / routing / ECO changes from Arena (or successor) without re-keying | Client update: Arena rationalization | Gateworks | 2.1 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-022 | Integration | Define system of record by function across GWTrack / NetSuite / Arena and eliminate duplicate masters | Client update | Gateworks | 2.1 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-023 | Integration | Integrate with floor equipment, test stations and label printers | GWTrack features | Gateworks | 1.3 / 2.1 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-024 | Compliance | Support ITAR / CUI handling: access by US-person, data residency and segregation | EL focus: ITAR / CUI | Gateworks | 2.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-025 | Compliance | Provide electronic records, audit trail and retention to meet customer / quality-system audits | Ops walk | Both | 2.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-026 | Security | Role-based access and segregation of duties for floor and office users | Ops walk | Both | 2.2 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-027 | Reporting | Provide real-time floor dashboards and daily operational reports (WIP, queue, shortages, yield) | GWTrack features | Both | 1.3 / 2.1 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-028 | Reporting | Ad hoc / saved reporting without developer support | Ops walk | Both | 2.1 / 3.4 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-029 | Performance | Station transactions respond within agreed time at peak load | Client update: keep performance | Both | 2.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-030 | Performance | Continue operating (or recover cleanly) when network / ERP is unavailable | Client update: keep automation | Gateworks | 2.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-031 | Automation | Preserve existing GWTrack automations (auto-transactions, auto-completes, auto-labeling) – list to be confirmed | Client update: keep automation | Gateworks | 1.3 / 2.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-032 | Scalability | Scale to additional users / lines / entities without redesign | EL / assessment: GWTrack not built to extend | Both | 2.3 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis
REQ-033 | Supportability | Vendor-supported platform with clear ownership; remove key-person risk | Ops walk | Gateworks | 2.1 |  |  |  | TBD | TBD | TBD |  |  | Hypothesis

## 2 Observations
Obs ID | Date | Site | Session | Observation (what we saw / heard) | Type | Impact | Related Req ID | Source person / role | Follow-up needed | Photo / artifact ref
OBS-001

## 3 Irvine Backlog
ID | Process step | Issue / pain point | Proposed optimization | Type (Config / Report / Custom / Process) | Value (H/M/L) | Effort (S/M/L) | Owner (Crowe / Y-Hire / Ezurio) | ADO work item # | Notes
IRV-001 | Allocation | Lines not fully committed / Special Order lines require manual reallocation before pick | [6 empty] | Validate frequency
IRV-002 | Pick | Partial pick closes task → reverse pick required to re-pick when stock arrives | [6 empty] | Validate
IRV-003 | Issue | Work Order Issue created manually; default inventory detail bin errors | [6 empty] | Who owns this step – QC vs. material handler?
IRV-004 | Production | No control preventing a run from starting without sufficient material or standard cost | [6 empty] | From Aug assessment
IRV-005 | Timekeeping | Timekeeping gaps in Manufacturing Mobile vs. Ezurio requirements | [6 empty] | Capture the requirement list
IRV-006 | Quality | RMA / rework / scrap tracked manually; QMS in SharePoint
IRV-007 | De-kit | Post-production reconciliation via templates + imports (IA / bin transfer / inventory transfer) | [6 empty] | Quantify effort
IRV-008 | Automation | Auto-Mark WOs Built workflow suspended 10/1 (error: BOM not defined for assembly item, WO 2447441) | [6 empty] | Why suspended? How are WOs closed now?

## 4 GWTrack Features
# | GWTrack capability | Demo'd? (Y/N) | How it works today (brief) | Automated vs. manual | Used by (role) | Frequency of use | Business-critical? (Y/N) | Where should it live? (GWTrack / NetSuite / Arena / MES / Retire) | Gap / risk in alternatives | Req ID
1 | Job / work order creation & release
2 | Routing / operation sequencing
3 | Work instructions / document display
4 | Station scanning / operator transactions
5 | Material availability check
6 | Kitting / component issue
7 | Backflush / consumption
8 | Lot / serial genealogy
9 | Test data capture
10 | Defect capture & coded reasons
11 | Defect heatmaps
12 | NCR / rework / scrap
13 | RMA handling
14 | CAPA / 8D
15 | Labor / time capture
16 | WIP tracking & visibility
17 | Inventory transactions to NetSuite
18 | Cost / variance data
19 | Label printing
20 | Equipment / test-station integration
21 | Dashboards / reports
22 | User roles & permissions
23 | Audit trail / e-records
24 | Arena / BOM-ECO interface

## 5 Option Scoring
Criteria weights sum to 100. Score each option 1 (poor) – 5 (excellent) after the onsite. Weighted score = SUMPRODUCT(weight, score)/100.
Criterion | Weight | A: Extend GWTrack | B: Mfg Mobile / Adv Mfg | C: 3rd-party MES / SuiteApp | Basis / evidence
Work execution & traceability fit | 15
Material availability / process control | 10
Standard cost enforcement | 5
Timekeeping / labor | 10
Quality tracking (defects, NCR, RMA, CAPA) | 15
ITAR / CUI & compliance fit | 15
Automation & performance retained | 10
Integration with NetSuite / Arena | 10
Scalability / supportability | 5
Estimated effort & risk of implementation | 5
TOTAL

## 6 Open Items
ID | Item | Owner | Due | Status
OI-001 | Confirm ITAR/CUI scope and what may be shared with non-US Crowe personnel (incl. Y-Hire / international staff) | Ezurio compliance / David England | Before 10/19 | Open
OI-002 | Confirm 'Jason' – role and written MES objectives | David England | Before 10/19 | Open
OI-003 | Confirm attendee names/roles for each session (agenda placeholders) | David England | Before 10/16 | Open
OI-004 | Pull current Irvine backlog from Azure DevOps (needs ADO org/project/PAT) | Jordan Piatek | Before 10/19 | Open
OI-005 | Confirm Y-Hire (Hana, Kyle) availability for Wed 10/21 AM given India working hours | Jordan Piatek | Before 10/16 | Open
OI-006 | Coverage for Tue 10/20 (Grant PTO) – Rohit leading technical sessions | Jordan / Grant | Before 10/19 | Open
OI-007 | Plan for draft distribution while Jordan is on PTO Oct 23 – Nov 2 | Jordan / Grant / Sohaa | 10/21 | Open
OI-008 | Data request sent to Ezurio (last page of the client agenda) | Jordan Piatek | 10/9 | Open
OI-010 | Agenda fix: Day 2 session 2.3 still starts 12:45 but lunch now runs 12:00–1:00 – confirm 2.3 = 1:00–2:45 | Jordan Piatek | Before sending agenda | Open
OI-009 | Confirm why Auto-Mark WOs Built workflow was suspended 10/1 and current WO closing process | Trevor Kanwal / Ezurio | Before 10/21 | Open